## Sheet1
Scope of Work and Bid Document
2303 SCHLEY AVE, SAN ANTONIO, TX 78210
Contractor to furnish all necessary permits, inspections, materials, labor and workmanship to install, construct, and place the improvements according to the specifications below.
Contractor is responsible for checking all plan notes. All work undertaken must meet City code and inspections.
All materials used to be new and manufactured within the last 12 months.
Construction to be completed within 120 days from start date of permit. Contractor to furnish one year warranty from date of completion.
Contractor to dispose of all debris, maintain a clean worksite during construction, and clean interior and exterior of property upon completion.
Bid Detail
EXTERIOR IMPROVEMENTS
Tree trimming and site prep, including haul off
Flatwork: driveway/carport and walkway to front door as per plans; flatwork finish – broom
Landscaping: add topsoil as needed to create a level yard; plant three (3) 1.5" caliper cedar elm trees (or the equivalent to meet COSA regulations)
Install wooden privacy fencing along sides and back of lot, with entrace gate on side
Install wood stairs at back porch
Clean exterior and make presentable for sale
|  |  | Subtotal | 0
FOUNDATION
To be completed as per plans and local building codes
Ensure sloped concrete approach to exterior doors (flush threshold at entryway required by COSA Universal Design Guidelines)
Pre-pour inspection by engineer required, inspection letter must be provided to NHSSA
Pay attention to "FOUNDATION NOTES"
Pay attention to "KEY NOTES"
Subtotal
FRAMING
To be completed as per plans and accordance with the Uniform Building Code and with city codes and ordinances
Add horizontal blocking for grab bars around all showers and toilets, approximately 33-36 inches above finished floor
Pay attention to "AIR BARRIER"
Pay attention to "GENERAL NOTES"
Subtotal
WINDOWS
New single hung, vinyl windows to be installed as per plans
Windows to be Better-Built, Croft or approved equal
Windows to be double pane, Low-E Efficient as per code with screens as per UDC
Check "GENERAL NOTES"
Install blinds on all windows (2-inch, faux wood, white)
Subtotal
ROOFING
#30 felt roof paper under 25-year asphalt shingles
Check "GENERAL NOTES"
Subtotal
PLUMBING (INLCUDING FIXTURES)
Plumbing and installation of all fixtures to be completed as per plans and in accordance with the Uniform Plumbing Code
Contractor reponsible for obtaining all permits and inspections as required by city and or state codes and ordinances
Fixtures to be as follows:
Delta faucets throughout
All brushed nickel fixtures
American Standard (or NHSSA-approved equivalent) for toilets and sinks
8” deep-26 gage double sink for kitchen
Water Heater to be GE or NHSSA-approved equivalent, energy efficient
Subtotal
HEATING & COOLING
Install a new HVAC unit as per plans and in accordance with the Uniform Plumbing Code
Contractor reponsible for obtaining all permits and inspections as required by city and or state codes and ordinances (if applicable)
Provide ventilation for appliances as needed, including those appliances supplied by the plumbing contractor
Contractor to size unit appropriately, as per plans
Subtotal
ELECTRICAL (INCLUDING FIXTURES & APPLIANCES)
Complete as per plans and relevant building codes
Contractor reponsible for obtaining all permits and inspections as required by city and or state codes and ordinances
Contractor will purchase and install all light fixtures and appliances
Light fixtures to be nickel/bronze or similar color of medium price
Appliances to be electric and will include refrigerator, dishwasher, stove/range, and microwave (above stove with exhaust fan)
NHSSA will choose light fixtures and appliances from sample selection provided by contractor
Control switch for stove exhaust fan must be installed in accessible location as per City of San Antonio's Universal Design Guidelines
Install a doorbell
Contractor to provide all labor and material for the connection of temporary service
Subtotal
CABINETS (BATH & KITCHEN)
Bathroom vanity and kitchen cabinets will be constructed of a hardwood frame and a plywood shaker style door panel (White)
Contractor to install handles/knobs on all cabinets and drawers
Subtotal
COUNTERTOPS
Countertops to be Formica or comparable. The counter will extent 1-inch past base cabinet.
NHSSA to choose color of countertops from sample selection provided by contractor
Contractor is responsible for all field measurements
Subtotal
SHOWER/BATH TILE
All tubs/showers to have white ceramic 3x6 subway tile surround
Subtotal
INSULATION
To be completed as per plans and local building codes
Check plan notes. Pay attention to "AIR BARRIER" and "GENERAL NOTES"
Window framing will be packed with loose insulation
All cracks in interior or exterior surfaces that may provide insect harborage after prime coat of paint but prior to finish coat will be sealed.
Subtotal
DRYWALL
To be completed as per plans
Drywall specifications:
All walls to be in accordance with city codes and outside corners to be square corner bead, including windows on all four sides
Texture will be orange peel
All drywall installation will be screwed/nailed to the studs using the appropriate length of drywall screws/nails and all screw and nail placement shall be in accordance with city codes and ordinances
Drywall to be ½ inch thick and moisture resistant in bathrooms
Check plans for additional notes
Subtotal
INTERIOR PAINT
Work to include one coat of primer, one coat of low luster acrylic enamel and caulking, puttying of all joints, baseboards, casing, shelving and other attachments to the walls
All wood materials will be paint grade, including doors, casing and baseboards, windowsills, window trims
Interior to have two colors (NHSSA to choose colors)
Subtotal
FINISH CARPENTRY
Work will include installation of all baseboards, door hardware (interior & exterior), shelving, closet hardware, outside corners on baseboard to cut and install to be set and ready for paint
Build reading bench in master bedroom, as per plans
Trim to be C-100
Subtotal
EXTERIOR SIDING & PAINT
Exterior to be fiber cement siding and trim
Exterior to have two colors (base and trim), selected by NHSSA
Subtotal
DOORS
Entrance door will be 1 ¾” thick metal with foam insulation and magnetic weather stripping, door to be painted NHSSA color choice. Threshold will be aluminum with factory installed vinyl sweep with aluminum sill or aluminum vinyl bubble. Jamb will be wood, caulked, primed and painted (color selected by NHSSA).
Pre-hung units will be used whenever possible. A keyed Deadbolt above the lockset will be installed. All locksets will be key alike.
Interior doors will be 6 panel painted white. All doors will be Stanley or owner-approved equivalent and will include doorknobs and doorstops.
Subtotal
FLOORING
Flooring to be luxury vinyl plank in kitchen, living areas, bedrooms, and hallways. Flooring in bathrooms and utility/laundry rooms to be ceramic tile. NHSSA to select colors and styles from sample provided by contractor. Cost to be mid-range, color to be brown or grey tones.
Subtotal
HARDWARE
Bathroom hardware will include shower curtain rod, toilet paper holder, towel ring, and towel bar (brushed nickel)
Mirrors to be installed above bathroom sinks
Subtotal
OTHER
Permits and fees (Note: this project has COSA FEE WAIVERS worth $854.00 and SAWS FEE WAIVERS worth $6,302.00; please reduce your costs by these amounts)
Termite treatment
Clean interior and make presentable for sale
Insurance (please see bid instructions for required coverages)
Overhead/profit
|  |  | Subtotal | 0
|  |  | TOTAL | 0
NHSSA to approve:
Color, quality and style of flooring
Color of interior and exterior paint
Color, quality and style of cabinets
Color, quality and style of countertops
Color, quality and style of light fixtures
Make & model of appliances
Scope of work and bid submitted by:
Name:
Signature:
Date: